## P1 Gap Tracker
P1 BRAND DEVELOPMENT — GAP ANALYSIS & TRACKING
15 Identified Gaps ¦ 5 HIGH+MEDIUM Closed ¦ 10 Remaining ¦ Updated March 2026
Gap ID | Severity | Document | Gap Description | Action Required | Status | Date Closed | Effort Est. | Notes
#8 | HIGH | P1D | B2B Pitch Deck: structure existed but NO word-for-word slide copy (headlines, subheads, speaker notes) | Write exact content for all 10 slides with headlines, data callouts, and speaker notes. Comprehensive enough for a designer to build without briefing. | ✅ CLOSED | Mar 2026 | 3-4 hrs | Added as P1D Section 8.2. All 10 slides now have word-for-word copy + speaker notes.
#10 | HIGH | P1C | No crisis communication plan for product failures, composting challenges, greenwashing accusations, or competitor attacks | Create 4-scenario crisis response framework with pre-written templates and escalation protocol. | ✅ CLOSED | Mar 2026 | 2-3 hrs | Added as P1C Section 15. 4 scenarios + 3-level escalation protocol.
#5 | MEDIUM-HIGH | P1B | Brand guidelines document listed as deliverable but table of contents and page-by-page structure not specified | Write 20-page brand guidelines outline: cover, story, logo (variants/rules), color (hex/RGB/CMYK/Pantone), typography, photography, voice, packaging, co-brand, digital assets, contact. | 🔴 OPEN |  | 1-2 hrs | Designer cannot produce guidelines without knowing page structure
#1 | MEDIUM | P1B | No formal brand positioning framework (For/Who/That/Unlike structure + 2x2 competitive positioning map) | Create Brand Positioning Canvas: For [target] Who [need] [Brand] is [category] That [benefit] Unlike [competitors]. Add 2x2 map plotting brand vs. Heatsheets, GreenGear, JOSANTO on Warmth vs. Sustainability axes. | 🔴 OPEN |  | 1-2 hrs | Strategic foundation document for all external communications
#3 | MEDIUM | P1B | QR code on packaging mentioned in GTM tracker but not specified: what it links to, tracking, user flow after scan | Specify: QR links to brand.com/scan with composting instructions + brand video + email capture. Use dynamic QR (QR.io) so URL can change without reprinting. Track scans as KPI (5-10% target). | 🔴 OPEN |  | 30 min | Critical for measuring packaging engagement and building post-purchase email list
#6 | MEDIUM | P1A+P1C | Tagline candidates duplicated across P1A (6 candidates) and P1C (8 candidates) with inconsistent rankings | Consolidate into ONE canonical list in P1C. Update P1A to cross-reference P1C for taglines. Deduplicate all unique taglines into unified priority ranking. | 🔴 OPEN |  | 30 min | Creates confusion for founder trying to select final tagline
#9 | MEDIUM | P1E+P0C | P0C's 53-race prioritized database not integrated with P1E's B2B prospect list from 7 additional sources | Add Section 5.3 to P1E: merge P0C Tier 1-3 races + P1E sources. Deduplicate. Enrich with RD contact info. Target: 75-100 unique prospects. | ✅ CLOSED | Mar 2026 | 1-2 hrs | Added as P1E Section 5.3. 7-step merge process with scoring. Target: 75-100 prospects.
#11 | MEDIUM | P1B | No accessibility & inclusivity guidelines: diversity in photography, alt text standards, ADA compliance, gender-neutral copy | Add Accessibility & Inclusivity section to P1B: alt text standards, diverse runner representation, gender-neutral language, WCAG 2.1 AA for landing page, honest sizing documentation. | 🔴 OPEN |  | 1 hr | Essential for brand integrity and legal compliance
#12 | MEDIUM | P1C/P1E | No post-launch email flows beyond welcome sequence (no cart abandonment, post-purchase, re-engagement, B2B nurture) | Write 4 automated flows: Cart Abandonment (3 emails/72hr), Post-Purchase (Day 3 how-to, Day 7 review, Day 14 referral), Re-engagement (Day 60 win-back), B2B Nurture (monthly case studies). | ✅ CLOSED | Mar 2026 | 3-4 hrs | Added as P1E Section 10. 4 complete flows with full email copy: cart abandon, post-purchase, re-engage, B2B nurture.
#13 | MEDIUM | P1C/P1D | No Amazon A+ Content plan (Enhanced Brand Content) — 3-10% conversion lift being left on the table | Plan 5 A+ modules: brand story header, 4-image feature grid, comparison chart (vs. garbage bag/Heatsheets/GreenGear), composting lifecycle infographic, FAQ. Requires Amazon Brand Registry. | 🔴 OPEN |  | 2-3 hrs | A+ Content increases conversion 3-10% per Amazon's own data
#14 | MEDIUM | P1E | No SEO/blog content strategy for Shopify organic traffic — $0 CAC channel being ignored entirely | Add SEO Foundation section to P1E: 10-15 target keywords, 4-6 blog article plan ('What to Wear at Marathon Start Line', 'How to Stay Warm Before a Race'), on-page checklist, 1 blog/week schedule. | ✅ CLOSED | Mar 2026 | 2-3 hrs | Added as P1E Section 11. 15 keywords, 6 blog articles with briefs, on-page SEO checklist, publishing cadence.
#2 | LOW-MEDIUM | P1B | No competitive logo visual analysis for designer reference — designer lacks context for what to differentiate from | Add 2-3 sentences per competitor describing logo types (icon shape, wordmark style, mark+type relationship). Add: 'Our logo should NOT be: a leaf, a globe, a recycling symbol.' | 🔴 OPEN |  | 30 min | Quick addition; prevents cliché logo design
#4 | LOW | P1C/P1B | Missing print production specs for B2B data sheet (bleed, safe zone, resolution, CMYK, paper stock) | Add paragraph: 8.5x11" final, 8.75x11.25" with bleed, 300 DPI, CMYK, 100lb recycled gloss, PDF/X-1a output. Print cost: $0.30-$0.60/sheet at 250+. | 🔴 OPEN |  | 15 min | Prevents production errors when sending to printer
#7 | LOW | P1D | No printable race-day photography shot checklist for chaotic race mornings | Add one-page appendix with 20-25 checkbox shots grouped by time window: Pre-Race, Corral, Start, Post-Start. | 🔴 OPEN |  | 30 min | Race mornings are chaotic; a checklist ensures no critical shots are missed
#15 | LOW | P1C | No international messaging adaptation notes (US-specific references need flagging for EU/UK/Canada expansion) | Add paragraph to P1C: Replace BPI with EN 13432 for EU. Swap US race examples for local races. 'Leave No Trace' may not resonate outside US. Prices need local currency. | 🔴 OPEN |  | 15 min | Quick future-proofing for Year 2 international expansion
TOTALS |  |  |  |  | 5 CLOSED / 10 OPEN |  | ~21-30 hrs total

## Task-by-Task Audit
P1 GTM TRACKER — 30 TASK AUDIT
19 Complete ¦ 7 Process-Only (Expected) ¦ 4 With Gaps ¦ Updated March 2026
Task ID | Task | Covered In | Status | Gap Ref | Notes
1.01 | Brainstorm 25+ brand name candidates | P1A Sec 2 | ✅ COMPLETE |  | 30+ candidates across 6 strategies — exceeds target
1.02 | USPTO trademark search top 10 | P1A Sec 4 | ⚠️ PROCESS ONLY |  | Framework provided; live TESS searches need execution
1.03 | Verify .com domain + social handles top 5 | P1A Sec 5 | ⚠️ PROCESS ONLY |  | Tools listed; live availability checks need execution
1.04 | Test 3-5 finalists via runner polls | P1A Sec 6 | ✅ FRAMEWORK |  | 5 channels, 8 criteria, 3-phase protocol — ready to execute
1.05 | File trademark application | P1A Sec 4.4 | ✅ COMPLETE |  | TEAS Plus/Standard, Classes 25+24, timeline
1.06 | Secure domain, social handles, Workspace | P1A Sec 5.2-5.3 | ✅ COMPLETE |  | Namechk/KnowEm + Google Workspace setup
1.07 | Define brand positioning | P1B Sec 1 | ✅ COMPLETE | Gap #1 | Statement exists; formal framework is Gap #1 (MEDIUM)
1.08 | Design logo: 3+ concepts | P1B Sec 5 | ⚠️ BRIEF ONLY | Gap #2 | Design brief ready; logo analysis is Gap #2 (LOW-MED)
1.09 | Develop color palette | P1B Sec 3 | ✅ COMPLETE |  | 8-color system with hex, usage rules, WCAG
1.10 | Design product packaging | P1B Sec 6 | ⚠️ BRIEF ONLY | Gap #3 | 5 components; QR strategy incomplete (Gap #3)
1.11 | Create co-brand template | P1B Sec 7 | ✅ COMPLETE |  | Template specs, drop zones, design rules
1.12 | Design sustainability data sheet | P1C Sec 8 | ✅ COMPLETE | Gap #4 | Content complete; print specs missing (Gap #4, LOW)
1.13 | Build brand guidelines document | P1B Sec 10.1 | ⚠️ UNDERSPECIFIED | Gap #5 | Referenced in timeline; no TOC/outline (Gap #5, MED-HIGH)
1.14 | Write brand origin story (250w + 50w) | P1C Sec 1 | ✅ COMPLETE |  | 3 versions: 250w DTC, 50w short, B2B
1.15 | Develop B2B messaging framework | P1C Sec 3 | ✅ COMPLETE |  | 7 messages + hierarchy + email template
1.16 | Develop DTC messaging framework | P1C Sec 4 | ✅ COMPLETE |  | 7 messages mapped to 3 personas
1.17 | Test 5+ tagline candidates | P1C Sec 5 + P1A Sec 7 | ⚠️ OVERLAP | Gap #6 | Candidates in both docs; need consolidation (Gap #6)
1.18 | Write Amazon/Shopify/B2B copy | P1C Sec 6-8 | ✅ COMPLETE |  | Amazon publication-ready; Shopify + B2B data sheet done
1.19 | Build impact messaging framework | P1C Sec 9 | ✅ COMPLETE |  | 7 levels, per-unit to industry scale, legal claims
1.20 | Storyboard 60-90s brand film | P1D Sec 1-2 | ✅ COMPLETE |  | 9-scene 90s + 6-scene 60s with timecodes/audio
1.21 | Produce brand film (production guide) | P1D Sec 3-4 | ✅ COMPLETE |  | 4 tiers ($0-$50K), 7 video cuts
1.22 | Capture race waste photography | P1D Sec 6 | ✅ COMPLETE | Gap #7 | 7-moment guide; printable checklist is Gap #7 (LOW)
1.23 | Create product photography | P1D Sec 5 | ✅ COMPLETE |  | 9-shot plan, Amazon 2026 compliant
1.24 | Create B2B pitch deck | P1D Sec 8 | ✅ CLOSED GAP | Gap #8 ✅ | 10-slide structure + FULL SLIDE COPY now included
1.25 | Build landing page with email capture | P1E Sec 1 | ✅ COMPLETE |  | 8-section blueprint + A/B test plan
1.26 | Set up email marketing + welcome sequence | P1E Sec 2-3 | ✅ COMPLETE |  | Klaviyo setup + 5-email framework (full copy in P1C)
1.27 | Seed pre-launch list (Reddit, FB, Strava) | P1E Sec 4 | ✅ COMPLETE |  | 8 channels with signup estimates
1.28 | Build B2B prospect list: 50+ race directors | P1E Sec 5 | ✅ COMPLETE | Gap #9 ✅ | 7 sources + spreadsheet + P0C merge guide. 75-100 target prospects.
1.29 | Create referral incentive program | P1E Sec 6 | ✅ COMPLETE |  | 3-tier program; runner-to-RD = gold channel
1.30 | Partner with 2-3 running influencers | P1E Sec 7 | ✅ COMPLETE |  | 5-tier strategy + outreach template + FTC compliance

## Priority Actions
P1 GAP CLOSURE — PRIORITY ACTION LIST
Ordered by Priority: Before Launch → 2 Weeks → 4 Weeks → Nice-to-Have
Priority | Gap(s) | Action | Effort | Status
🔴 BEFORE LAUNCH | #8 | Write word-for-word pitch deck slide copy (10 slides, headlines, speaker notes) | 3-4 hrs | ✅ CLOSED
🔴 BEFORE LAUNCH | #10 | Create crisis communication response templates (4 scenarios + escalation protocol) | 2-3 hrs | ✅ CLOSED
🔴 BEFORE LAUNCH | 1.02+1.03 | Run live USPTO TESS searches + domain/handle checks for Top 10 names | 2-3 hrs | 🔴 OPEN
🟠 WITHIN 2 WEEKS | #5 | Write full brand guidelines table of contents (20-page structure) | 1-2 hrs | 🔴 OPEN
🟠 WITHIN 2 WEEKS | #12 | Write post-launch email flows (cart abandon, post-purchase, re-engage, B2B nurture) | 3-4 hrs | ✅ CLOSED
🟠 WITHIN 2 WEEKS | #13 | Plan Amazon A+ Content (5 modules: brand story, features, comparison, lifecycle, FAQ) | 2-3 hrs | 🔴 OPEN
🟡 WITHIN 4 WEEKS | #1 | Create formal Brand Positioning Canvas + 2x2 competitive positioning map | 1-2 hrs | 🔴 OPEN
🟡 WITHIN 4 WEEKS | #3 | Specify QR code destination, tracking, and user flow for packaging | 30 min | 🔴 OPEN
🟡 WITHIN 4 WEEKS | #6 | Consolidate tagline candidates into single canonical list in P1C | 30 min | 🔴 OPEN
🟡 WITHIN 4 WEEKS | #9 | Merge P0C 53-race database with P1E B2B prospect list | 1-2 hrs | ✅ CLOSED
🟡 WITHIN 4 WEEKS | #11 | Add accessibility & inclusivity guidelines to P1B | 1 hr | 🔴 OPEN
🟡 WITHIN 4 WEEKS | #14 | Create SEO/blog content strategy for Shopify organic traffic | 2-3 hrs | ✅ CLOSED
🟢 NICE-TO-HAVE | #2 | Add competitive logo visual analysis (2-3 sentences per competitor) | 30 min | 🔴 OPEN
🟢 NICE-TO-HAVE | #4 | Add print production specs for B2B data sheet | 15 min | 🔴 OPEN
🟢 NICE-TO-HAVE | #7 | Create printable race-day photography shot checklist | 30 min | 🔴 OPEN
🟢 NICE-TO-HAVE | #15 | Add international messaging adaptation notes to P1C | 15 min | 🔴 OPEN